## Sheet1
DATE | TASK |  | ASSIGNED TO | Status
2023-12-08 | PROJECT | CASE STUDY DISCUSSION | ALL TEAM | Done
|  | OVERALL PLANNING | ALL TEAM | Done
2023-12-09 | WEB API | DISCUSSED AND PLANNED METHODS TO BE USED IN API | Kiran, Yogesh, Gangadhar | Done
| ANGULAR | INITIATED PROJECT IN ANGULAR : Created login and AdminLogin Screens | Kiran, Sai Prakash, Suresh | Done
| DATA BASE | PAPERWORK : DATABASE DESIGN : Entities and ERR Diagram | Rohit, Suresh, Yogesh | Done
| AZURE | WE DISSCUSS ABOUT WHAT IS BLOB STORAGE AND WHERE WE USING IN OUR PROJECT | All TEAM | Done
2023-12-10 | ANGULAR | LOGIN SCREEN DISCUSSION AND DESIGNS ON PAPER: finalisation of designs | Kiran, Suresh | Done
| WEB API | CODE FIRST APPROACH .NETCORE WEB API | Yogesh, Gangadhar | Done
| AZURE | WE IMPLEMENTED BASIC BLOB STORAGE IN AZURE PORTAL | Rohit, Suresh, Yogesh | Done
| DATABASE | DATABASE AND DESIGING SETUP | Kiran | Done
2023-12-11 | ANGULAR | FULLY WORKING LOGIN SCREEN, REGISTER USER, FORGOT PASSWORD USING HARD CODED VALUES | Kiran, Rohit | Done
| WEB API | DISUCSSION ON METHODS AND CONTROLLERS | Gangadhar,Suresh | Done
| AZURE | DISSCUSS ABOUT WEB APPS AND AZURE SQL IMPLEMENTATION REQUIRED FOR PROJECT | Yogesh,Sai Prakash | Done